Timetable for Application and Selection procedures for the OSI / Chevening / University of Oxford 2006/07 Intake Scholarships

| Date | Action |
| --- | --- |
| 2005 |  |
| Monday 3 October | Funders to agree on scheme and all relevant documents (text of adverts and web site information, scholarship advert and scholarship notes). OSI/B to prepare email list of people/organisations to be informed of the new scholarship competition. Criteria guidelines in the form of a check list for the short-listing of applicants to be produced by OSI/B and FCO. |
| Monday 10 October | Oxford to email the approved documents (scholarship advert, scholarship guidance notes, application materials) to the local foundations, OSI/B and the British Council Manchester. |
| Monday 17 October | National foundations to forward copies of the materials to the local British Embassy and British Council. |
| Monday 24 October | Scholarships Scheme advertised in the relevant countries by the national foundations. Oxford to update its web pages. In addition, OSI/B to update its own web and send out details of the scheme by email to interested parties. |
| 2006 |  |
| Friday 6 January | Deadline for the receipt of applications by local foundations. Applicants requested to send original, plus one copy. |
| Friday 13 January | Deadline for national foundations to send on the received applications by courier to the Graduate Admissions Office (national foundations to retain one copy). The application must arrive at the Graduate Admissions Office by Friday 20 January 2006. In addition, national foundations to forward to Oxford by email (Laura.Thomlinson@conted.ox.ac.uk) a spreadsheet listing the names and addresses of the applicants. Also email a copy of the spreadsheet to OSI/B. |
| Friday 3 February | Shortlist to be prepared by the Director of the Master’s Programme at University of Oxford, ranking applicants in each country according to the given criteria checklist (reflecting OSI/FCO priorities). |
| Monday 6 February | Oxford to send copies of short-listed application forms to OSI/British Council Manchester and to inform foundations by email of short-listed applicants. National foundations to invite the applicants for interview and English language test (TOEFL or IELTS). Letters to unsuccessful applicants to be prepared by Oxford and sent directly to students (with copies to local foundations and OSI/B). |
| February | Interviews and Language Testing of all shortlisted applicants. Interview panel to consist of: Representative of British Embassy Representative of OSI (chosen by local foundation) (The dates for the tests and interviews should be arranged well in advance and applicants should be informed. Once the shortlist is known national foundations should give a copy of all applications to both the British Embassy representative and the OSI local representative, at least one week before the interviews.) |
| March | Co-ordinators to fax results of the interviews as well as language test results to Oxford, OSI and British Council Manchester as soon as they are available. |
| Friday 17 March | University of Oxford to propose list of awards (plus reserve applicants) to OSI / British Council Manchester. |
| Friday 31 March | List of awards and reserve applicants to be agreed between all 3 funders by this date. |
| Monday 3 April | Oxford to send out offer letters and details of funding directly to students (with copies to local foundations and OSI/B). Letters to unsuccessful interviewees to be prepared by Oxford and forwarded to local foundations for distribution. |
| Monday 1 May | All acceptances to be confirmed (and reserves offered awards, as appropriate). |
| Monday 15 May | OSI/B to produce its formal award letters for successful applicants. |
| June | OSI/B to distribute its award letters at the OSI Co-ordinators’ conference. |
| June/July | National Foundations to liaise with scholars to arrange travel for scholars to the UK. |